## Sheet1
CAR Roadmap
Friday, January 7, 2022
11:17
CAR Dashboards: Phase I
Dashboard Name | Description | Dev Status | Audit Status | In Prod? | Widget Name | Widget added? | Standalone Dashboard built | Deployed to all Customers
Spend Management | From Parts and Repairs Spend sheet on CAR | Complete | 99.9% | Yes | Spend Management | Yes | No | Yes
Quality Management | From Quality Management sheet on CAR | Complete | 99.9% | Yes | Quality Management | Yes | No | Yes
Order Fill Rate | From Service Level Metrics sheet | Complete | 100% | Yes | Order Fill Rate | No | Yes | Yes
Response Time | From Service Level Metrics sheet | Complete | 100% | Yes | Response Rate | No | Yes | Yes
Quote Rate | From Service Level Metrics sheet | Complete | 100% | Yes | Quote Rate | No | Yes | Yes
On Time Order Processing | From Service Level Metrics sheet | Complete | 100% | Yes | On Time Order Processing | No | Yes | Yes
Customer Savings From Market Price | From PS PRO value sheet on CAR | Complete | 100% | No, ready to go to Prod | Savings from Market Price | No | No | Yes
Customer Net Hard Savings | Form Net Hard Cost Savings, sheet on CAR | Complete | 50% | No | Net Hard Savings | No | No | Yes
Biomed Shipping and Inventory | From Biomed Shipping and Inventory, Overnight Biomed Inventory | Needs Changes | 50% | No | Biomed Shipping and Inventory | No | No | Yes
Program Performance | From Program Performance sheet on CAR | Needs Changes | 18% | No | Program Performance | No | No | Yes
Gap to PS Pro Revenue Target / Spend Analysis Results | From Performance to Spend Analysis on CAR | Needs Changes | 0% | No | Performance to Spend Analysis | No | No | Yes
On Time Delivery | From The On Time Delivery sheet on CAR | Needs Changes | 0% | No | On Time Delivery | No | No | No
Consolidate Your Orders | From the Consolidate your Orders sheet on CAR (The Pivot table already exists in the Inventory dashboard) | Not Complete | 0% | No | Consolidate your Orders | No | No | Yes
Customer Apollo Landing Page | This will include drill thru widgets for all the above | Not Complete | 0% | Yes* | N/A | N/A | N/A | Yes
CAR Excel workbook:
CAR Sheet Name | Recreated as Dashboard | Dashboard Dev Status | Completion | In Prod? | Name of Widget on Customer Landing Page | Deployed to all Customers? | Customers
Parts and Repairs Spend | Spend Management | Complete | 100% | Yes | Spend Management | Yes
Key Savings Opportunities | Spend Management | Complete | 100% | Yes | Net Hard Savings | Yes
Quality Management | Quality Management | Complete | 100% | Yes | Quality Management | Yes
Service Level Metrics | 4 dashboards in prod | Complete | 100% | Yes | Quote Rate, Response Time, Order Fill Rate, On Time Order Processing | Yes
Not Able to Quote | Quote Rate | Complete | 100% | Yes | Quote Rate | Yes
Assumptions | Included in CARSA, which is loaded to DW, utilized in many dashboards | Complete | 100% | Yes | N/A | Yes
User Level Activity Reporting | Incorporated as a filter into many dashboards | Complete | 100% | Yes | N/A | Yes
Overnight Biomed Inventory | Inventory Management | Complete | 80% | No | Inventory Management | Yes
Biomed Shipping and Inventory | Inventory Management | Complete | 80% | No | Inventory Management | Yes
Net Hard Cost Savings | Customer Net Hard Savings | Complete | 50% | No | Net Hard Savings | Yes
Extraordinary Biomed Savings | Customer Net Hard Savings | Complete | 50% | No | Net Hard Savings | Yes
Extraordinary Imaging Savings | Customer Net Hard Savings | Complete | 50% | No | Net Hard Savings | Yes
Missed Savings | Customer Net Hard Savings | Complete | 50% | No | Net Hard Savings | Yes
Pre-existing Discounts | Incorporated in Customer Savings | Complete | 100% |  | N/A | Yes
Performance to Spend Analysis | Gap to PS Pro Revenue Target / Spend Analysis Results | Not Complete | 0% | No | Performance to Spend Analysis | Yes
Parts Spend By Facility | Gap to PS Pro Revenue Target / Spend Analysis Results | Not Complete | 0% | No | Performance to Spend Analysis | Yes
On Time Delivery | On Time Delivery | Not Complete | 0% | No | On Time Delivery | No | ?
Utilization | Program Participation and Productivity | Complete |  | No | Program Participation | Yes
Program Performance | Program Participation | Complete | 0% | No | Program Participation | Yes
Consolidate Your Orders | Consolidate Your Orders | Not Complete | 0% | No | Consolidate Your Orders | Yes
OEM List Price Accuracy | Still need to get it into existing dashboards | Not Complete | 0% | No | N/A | Yes
Dashboard Name | Status
Depot Repair | Not Started
Productivity | Not Started
Predictive Analytics to Eliminate OEM Contracts | Not Started
Formulary Impact | Not Started
On Site Service | Not Started
Contract Pro Reporting | Not Started
Insurance Reporting | Not Started